## Sheet1
Employee Name | Week Ending Date | Date Created | Project Name | Task Id | Brief Task Description | Est.Start Date | Est.End Date | Est. Time | Act. Time | Actual Start Date | Actual End Date | % completed | Status | Comments
Raj Kumar | 2023-01-07 | 2023-01-05 |  | TS01 | create form control for permanet address | 2023-01-05 | 2023-01-05 | 2hrs | 2hrs | 2023-01-05 | 2023-01-05 | 100% | completed
Raj Kumar | 2023-01-07 | 2023-01-05 |  | TS02 | Enable Photo Option in Survey Details Screen | 2023-01-05 | 2023-01-05 | 3hrs | 3hrs | 2023-01-05 | 2023-01-05 | 100% | completed
Raj Kumar | 2023-01-07 | 2023-01-05 |  | TS03 | Add user option in usermanagement screee | 2023-01-05 | 2023-01-05 | 3hrs | 3hrs | 2023-01-05 | 2023-01-05 | 100% | completed
Raj Kumar | 2023-01-07 | 2023-01-06 |  | TS04 | Create download option to download survey details | 2023-01-06 | 2023-01-06 | 3hrs | 3hrs | 2023-01-06 | 2023-01-06 | 100% | completed
Raj Kumar | 2023-01-07 | 2023-01-06 |  | TS05 | Filter option to filter survey by surveyee name start and end date,survey ID | 2023-01-06 | 2023-01-06 | 3hrs | 3hrs | 2023-01-06 | 2023-01-06 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-01-06 |  | TS06 | Testing and Deployment of the application | 2023-01-06 | 2023-01-06 | 3hrs | 3hrs | 2023-01-06 | 2023-01-06 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-20 |  | TS07 | Learning react native | 2023-03-20 | 2023-03-20 | 2hrs | 2hrs | 2023-03-20 | 2023-03-20 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-20 |  | TS08 | Learning react native | 2023-03-20 | 2023-03-20 | 2hrs | 2hrs | 2023-03-20 | 2023-03-20 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-20 |  | TS09 | Date field code review in xamarin | 2023-03-20 | 2023-03-20 | 2hrs | 2hrs | 2023-03-20 | 2023-03-20 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-20 |  | TS10 | Date field code refactor | 2023-03-20 | 2023-03-20 | 2hrs | 2hrs | 2023-03-20 | 2023-03-20 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-21 |  | TS11 | Date field code refactor | 2023-03-21 | 2023-03-21 | 2hrs | 2hrs | 2023-03-21 | 2023-03-21 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-21 |  | TS12 | Code review | 2023-03-21 | 2023-03-21 | 2hrs | 2hrs | 2023-03-21 | 2023-03-21 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-21 |  | TS13 | Changing suggested change and update stored procedure | 2023-03-21 | 2023-03-21 | 2hrs | 2hrs | 2023-03-21 | 2023-03-21 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-21 |  | TS14 | Learning react native | 2023-03-21 | 2023-03-21 | 2hrs | 2hrs | 2023-03-21 | 2023-03-21 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-22 |  |  | Ugadi holiday | 2023-03-22
Raj Kumar | 2023-03-25 | 2023-03-23 |  | TS15 | Learning react native | 2023-03-23 | 2023-03-23 | 2hrs | 2hrs | 2023-03-23 | 2023-03-23 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-23 |  | TS16 | MyDay Bug fix | 2023-03-23 | 2023-03-23 | 2hrs | 2hrs | 2023-03-23 | 2023-03-23 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-23 |  | TS17 | ksfc project setup | 2023-03-23 | 2023-03-23 | 2hrs | 2hrs | 2023-03-23 | 2023-03-23 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-23 |  | TS18 | ksfc project setup documentation | 2023-03-23 | 2023-03-23 | 2hrs | 2hrs | 2023-03-23 | 2023-03-23 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-24 |  | TS19 | KSFC legal documentation design document preparation | 2023-03-24 | 2023-03-24 | 3hrs | 3hrs | 2023-03-24 | 2023-03-24 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-24 |  | TS20 | Explanation about ksfc project | 2023-03-24 | 2023-03-24 | 2hrs | 2hrs | 2023-03-24 | 2023-03-24 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-24 |  | TS21 | disable acquired date to take upto today date | 2023-03-24 | 2023-03-24 | 2hrs | 2hrs | 2023-03-24 | 2023-03-24 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-25 |  | TS22 | Testing ksfc Acquired date field | 2023-03-25 | 2023-03-25 | 2hrs | 2hrs | 2023-03-25 | 2023-03-25 | 100% | completed
Raj Kumar | 2023-03-25 | 2023-03-25 |  | TS23 | Add new column to idmdspcharge table on update of deed number | 2023-03-25 | 2023-03-25 | 3hrs | 3hrs | 2023-03-25 | 2023-03-25 | 100% | completed
Raj Kumar | 2023-03-26 | 2023-03-26 |  |  | Sunday | 2023-03-26
Raj Kumar | 2023-04-01 | 2023-03-27 |  | TS24 | Add Not applicable button to security charge | 27-03-20233 | 27-03-20233 | 2hrs | 2hrs | 27-03-20233 | 27-03-20233 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-27 |  | TS25 | on click of not applicable security charge should not not appear in check list | 27-03-20233 | 27-03-20233 | 2hrs | 2hrs | 27-03-20233 | 27-03-20233 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-27 |  | TS26 | Karmani filter bug fix | 27-03-20233 | 27-03-20233 | 2hrs | 2hrs | 27-03-20233 | 27-03-20233 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-27 |  | TS27 | Karmani deployment | 27-03-20233 | 27-03-20233 | 2hrs | 2hrs | 27-03-20233 | 27-03-20233 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-28 |  | TS28 | Karmani Production deployment Design Document | 2023-03-28 | 2023-03-28 | 3hrs | 3hrs | 2023-03-28 | 2023-03-28 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-28 |  | TS29 | Not applicable button should not appear if Request lettor number exist | 2023-03-28 | 2023-03-28 | 3hrs | 3hrs | 2023-03-28 | 2023-03-28 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-28 |  | TS30 | Code review KSFC | 2023-03-28 | 2023-03-28 | 2hrs | 2hrs | 2023-03-28 | 2023-03-28 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-29 |  | TS31 | KSFC dsbcharge insertion bug fix | 2023-03-29 | 2023-03-29 | 2hrs | 2hrs | 2023-03-29 | 2023-03-29 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-29 |  | TS32 | Karmani database backup design document | 2023-03-29 | 2023-03-29 | 2hrs | 2hrs | 2023-03-29 | 2023-03-29 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-29 |  | TS33 | Ksfc Promoter Bank details insertion bug fix | 2023-03-29 | 2023-03-29 | 2hrs | 2hrs | 2023-03-29 | 2023-03-29 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-29 |  | TS34 | When Security charge is reedited Security charge should reappear in check list | 2023-03-29 | 2023-03-29 | 2hrs | 2hrs | 2023-03-29 | 2023-03-29 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-30 |  | TS35 | Make the Asset value from 20 ,00,000 under cersai registration Register and view | 2023-03-30 | 2023-03-30 | 2hrs | 2hrs | 2023-03-30 | 2023-03-30 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-30 |  | TS36 | Karmani wrong count issue discussion | 2023-03-30 | 2023-03-30 | 2hrs | 2hrs | 2023-03-30 | 2023-03-30 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-30 |  | TS37 | Update deed insertion bug fix | 2023-03-30 | 2023-03-30 | 2hrs | 2hrs | 2023-03-30 | 2023-03-30 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-30 |  | TS38 | Helping Jayanth and Srinivas | 2023-03-30 | 2023-03-30 | 2hrs | 2hrs | 2023-03-30 | 2023-03-30 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-31 |  | TS39 | make the site/plot field in change change of asset to to take only numbers,alphabets,/\-_ | 2023-03-31 | 2023-03-31 | 2hrs | 2hrs | 2023-03-31 | 2023-03-31 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-31 |  | TS40 | Send other relaxation as new Model to save in table | 2023-03-31 | 2023-03-31 | 2hrs | 2hrs | 2023-03-31 | 2023-03-31 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-31 |  | TS41 | Taking note KSFC Deployment | 2023-03-31 | 2023-03-31 | 2hrs | 2hrs | 2023-03-31 | 2023-03-31 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-03-31 |  | TS42 | Karmani issue Review | 2023-03-31 | 2023-03-31 | 2hrs | 2hrs | 2023-03-31 | 2023-03-31 | 100% | completed
Raj Kumar | 2023-04-01 | 2023-04-01 |  | TS43 | KSFC Meeting | 2023-04-01 | 2023-04-01 | 1hrs | 1hrs | 2023-04-01 | 2023-04-01 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-02 |  |  | Sunday | 2023-04-02
Raj Kumar | 2023-04-08 | 2023-04-03 |  | TS44 | if complience is yes and whether relaxation is no enable view in uc7 | 2023-04-03 | 2023-04-03 | 2hrs | 2hrs | 2023-04-03 | 2023-04-03 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-03 |  | TS45 | if complience is No and whether relaxation is no disable view in uc7 | 2023-04-03 | 2023-04-03 | 2hrs | 2hrs | 2023-04-03 | 2023-04-03 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-03 |  | TS46 | if complience is No and whether relaxation is Yes and is relaxed enable view in uc7 | 2023-04-03 | 2023-04-03 | 2hrs | 2hrs | 2023-04-03 | 2023-04-03 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-03 |  | TS47 | view in uc7 should be enable only when sum disbursement condition and additional condition is equal to number of relaxed condition | 2023-04-03 | 2023-04-03 | 2hrs | 2hrs | 2023-04-03 | 2023-04-03 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-04 |  | TS48 | In UC4 in all table Security Created should be same as Actual cost for first row (KSFC) | 2023-04-04 | 2023-04-04 | 3hrs | 3hrs | 2023-04-04 | 2023-04-04 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-04 |  | TS49 | In UC4 in all table Security Created should be added with Actual cost except first row (KSFC) | 2023-04-04 | 2023-04-04 | 3hrs | 3hrs | 2023-04-04 | 2023-04-04 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-04 |  | TS50 | Change requirement in last two tabs of UC4 (KSFC) | 2023-04-04 | 2023-04-04 | 1hrs | 1hrs | 2023-04-04 | 2023-04-04 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-04 |  | TS51 | debugging (KSFC) | 2023-04-04 | 2023-04-04 | 1hrs | 1hrs | 2023-04-04 | 2023-04-04 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-05 |  | TS52 | Add two Radio btn for field staff and hierarchy in add entity (MY DAY) | 2023-04-05 | 2023-04-05 | 2hrs | 2hrs | 2023-04-05 | 2023-04-05 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-05 |  | TS53 | hierarcy is normal flow of the app (MY DAY) | 2023-04-05 | 2023-04-05 | 2hrs | 2hrs | 2023-04-05 | 2023-04-05 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-05 |  | TS54 | In fieldstaff selection hierarcy is loded based on selectef field staff | 2023-04-05 | 2023-04-05 | 2hrs | 2hrs | 2023-04-05 | 2023-04-05 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-05 |  | TS55 | Testing and debugging | 2023-04-05 | 2023-04-05 | 2hrs | 2hrs | 2023-04-05 | 2023-04-05 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-06 |  | TS56 | In fieldstaff selection hierarcy is loded based on selectef field staff | 2023-04-06 | 2023-04-06 | 3hrs | 3hrs | 2023-04-06 | 2023-04-06 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-06 |  | TS57 | bug fix | 2023-04-06 | 2023-04-06 | 3hrs | 3hrs | 2023-04-06 | 2023-04-06 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-06 |  | TS58 | Testing and debugging | 2023-04-06 | 2023-04-06 | 2hrs | 2hrs | 2023-04-06 | 2023-04-06 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-07 |  | TS59 | If employee is selected any one of his corresponding hierarcal place should be loaded | 2023-04-07 | 2023-04-07 | 3hrs | 3hrs | 2023-04-07 | 2023-04-07 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-07 |  | TS60 | testing and debugging | 2023-04-07 | 2023-04-07 | 2hrs | 2hrs | 2023-04-07 | 2023-04-07 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-07 |  | TS61 | watching chair role mapping video | 2023-04-07 | 2023-04-07 | 2hrs | 2hrs | 2023-04-07 | 2023-04-07 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-08 |  | TS62 | Add two Radio btn for field staff and hierarchy in add entity (MY DAY) | 2023-04-08 | 2023-04-08 | 2hrs | 2hrs | 2023-04-08 | 2023-04-08 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-08 |  | TS63 | By Default, all Agreements# and Employee Names (Only Active Employees) Should be loaded. | 2023-04-08 | 2023-04-08 | 2hrs | 2hrs | 2023-04-08 | 2023-04-08 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-08 |  | TS64 | Based on Agreement Selected populate Entity Names/Codes | 2023-04-08 | 2023-04-08 | 2hrs | 2hrs | 2023-04-08 | 2023-04-08 | 100% | completed
Raj Kumar | 2023-04-08 | 2023-04-08 |  | TS65 | If Office Hierarchy is checked then the existing flow is continued i.e., Employee Name field is loaded based on Office Hierarchy | 2023-04-08 | 2023-04-08 | 2hrs | 2hrs | 2023-04-08 | 2023-04-08 | 100% | completed
Raj Kumar |  | 2023-04-09 |  |  | Sunday | 2023-04-09
Raj Kumar | 2023-04-15 | 2023-04-10 |  | TS66 | debugging Add Issue return (MY DAY) | 2023-04-10 | 2023-04-10 | 2.5hrs | 2.5hrs | 2023-04-10 | 2023-04-10 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-10 |  | TS67 | Meeting (KSFC) | 2023-04-10 | 2023-04-10 | 1.5hrs | 1.5hrs | 2023-04-10 | 2023-04-10 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-10 |  | TS68 | MyDay Design Document | 2023-04-10 | 2023-04-10 | 2.5hrs | 2.5hrs | 2023-04-10 | 2023-04-10 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-10 |  | TS69 | Ksfc UI changes & Meeting with Dinesh Sir | 2023-04-10 | 2023-04-10 | 1.5hrs | 1.5hrs | 2023-04-10 | 2023-04-10 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-11 |  | TS70 | Calculation of total amount in creation of disbusement proposal | 2023-04-11 | 2023-04-11 | 4hrs | 4hrs | 2023-04-11 | 2023-04-11 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-11 |  | TS71 | Helping Jayanth and Srinivas | 2023-04-11 | 2023-04-11 | 2hrs | 2hrs | 2023-04-11 | 2023-04-11 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-11 |  | TS72 | testing and debugging | 2023-04-11 | 2023-04-11 | 2hrs | 2hrs | 2023-04-11 | 2023-04-11 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-12 |  | TS73 | Helping Jayanth and Srinivas | 2023-04-12 | 2023-04-12 | 2hrs | 2hrs | 2023-04-12 | 2023-04-12 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-12 |  | TS74 | Disable Send approval until all complience is YES in conditions | 2023-04-12 | 2023-04-12 | 2hrs | 2hrs | 2023-04-12 | 2023-04-12 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-12 |  | TS75 | On Create of deed in leagal documentation one row should be inserted in tbl_hypoth_map and 2 row in tbl_hypoth _deed | 2023-04-12 | 2023-04-12 | 2hrs | 2hrs | 2023-04-12 | 2023-04-12 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-12 |  | TS76 | Testing and debugging | 2023-04-12 | 2023-04-12 | 2hrs | 2hrs | 2023-04-12 | 2023-04-12 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-13 |  | TS77 | watching chair role mapping video | 2023-04-13 | 2023-04-13 | 2.5hrs | 2.5hrs | 2023-04-13 | 2023-04-13 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-13 |  | TS78 | Helping Jayanth and Srinivas | 2023-04-13 | 2023-04-13 | 3hrs | 3hrs | 2023-04-13 | 2023-04-13 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-13 |  | TS79 | SonarQube setup | 2023-04-13 | 2023-04-13 | 2.5hrs | 2.5hrs | 2023-04-13 | 2023-04-13 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-14 |  | TS80 | Helping Jayanth and Srinivas | 2023-04-14 | 2023-04-14 | 3hrs | 3hrs | 2023-04-14 | 2023-04-14 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-14 |  | TS81 | Discussing Project requirement | 2023-04-14 | 2023-04-14 | 2hrs | 2hrs | 2023-04-14 | 2023-04-14 | 100% | completed
Raj Kumar | 2023-04-15 | 2023-04-15 |  | TS84 | No Tasks | 2023-04-15 | 2023-04-15 | 0 | 0 | 2023-04-15 | 2023-04-15 | 0 | null
Raj Kumar |  | 2023-04-16 |  |  | Sunday
Raj Kumar | 2023-04-22 | 2023-04-17 |  | TS85 | My Day Change requirement | 2023-04-17 | 2023-04-17 | 3hrs | 3hrs | 2023-04-17 | 2023-04-17 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-17 |  | TS86 | KSFC popup design | 2023-04-17 | 2023-04-17 | 2hrs | 2hrs | 2023-04-17 | 2023-04-17 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-17 |  | TS87 | Helping Jayanth and Srinivas | 2023-04-17 | 2023-04-17 | 3hrs | 3hrs | 2023-04-17 | 2023-04-17 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-18 |  | TS88 | No Tasks | 2023-04-18 | 2023-04-18 | 1hrs | 1hrs | 2023-04-18 | 2023-04-18 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-19 |  | TS89 | Learning Django | 2023-04-19 | 2023-04-19 | 2hrs | 2hrs | 2023-04-19 | 2023-04-19 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-19 |  | TS90 | Make the popup of ksfc movable | 2023-04-19 | 2023-04-19 | 4hrs | 4hrs | 2023-04-19 | 2023-04-19 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-19 |  | TS91 | My Day Discussion | 2023-04-19 | 2023-04-19 | 1hrs | 1hrs | 2023-04-19 | 2023-04-19 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-20 |  | TS92 | KSFC Meeting | 2023-04-20 | 2023-04-20 | 3hrs | 3hrs | 2023-04-20 | 2023-04-20 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-20 |  | TS93 | Helping Jayanth and Srinivas | 2023-04-20 | 2023-04-20 | 2hrs | 2hrs | 2023-04-20 | 2023-04-20 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-20 |  | TS94 | KSFC Task id 217 | 2023-04-20 | 2023-04-20 | 2hrs | 2hrs | 2023-04-20 | 2023-04-20 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-21 |  | TS95 | Create Other Relaxation tab | 2023-04-21 | 2023-04-21 | 2hrs | 2hrs | 2023-04-21 | 2023-04-21 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-21 |  | TS96 | Helping Jayanth and Srinivas | 2023-04-21 | 2023-04-21 | 2hrs | 2hrs | 2023-04-21 | 2023-04-21 | 100% | completed
Raj Kumar | 2023-04-22 | 2023-04-21 |  | TS97 | when Other relaxation is relaxed it should reflect in Disbursment | 2023-04-21 | 2023-04-21 | 3hrs | 3hrs | 2023-04-21 | 2023-04-21 | 80% | Incomplete
Raj Kumar | 2023-04-22 | 2023-04-22 |  | TS98 | My Day UI Chnages | 2023-04-22 | 2023-04-22 | 2hrs | 2hrs | 2023-04-22 | 2023-04-22 | 100% | completed
Raj Kumar |  | 2023-04-23 |  |  | Sunday
Raj Kumar | 2023-04-29 | 2023-04-24 | KSFC | TS99 | when Other relaxation is relaxed it should reflect in Disbursment | 2023-04-24 | 2023-04-24 | 3hrs | 3hrs | 2023-04-24 | 2023-04-24 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-24 | KSFC | TS100 | In Cersai tab date of registration should not excee date of execution of collateral security | 2023-04-24 | 2023-04-24 | 2hrs | 2hrs | 2023-04-24 | 2023-04-24 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-24 | KSFC | TS101 | The manipulation of the 'Amount'/ 'Cost' in these tabs should match the 'Total Project Cost' of the project, in case of any miss match, the system should display the alert message for the respective tab that the total amount/ cost of the items does not match with the total project cost. | 2023-04-24 | 2023-04-24 | 2hrs | 2hrs | 2023-04-24 | 2023-04-24 | 60% | InComplete
Raj Kumar | 2023-04-29 | 2023-04-25 | KSFC | TS102 | The manipulation of the 'Amount'/ 'Cost' in these tabs should match the 'Total Project Cost' of the project, in case of any miss match, the system should display the alert message for the respective tab that the total amount/ cost of the items does not match with the total project cost. | 2023-04-25 | 2023-04-25 | 3hrs | 3hrs | 2023-04-25 | 2023-04-25 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-25 | KSFC | TS103 | Testing And Debugging | 2023-04-25 | 2023-04-25 | 2hrs | 2hrs | 2023-04-25 | 2023-04-25 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-25 | KSFC | TS104 | Submit button in other relaxation should be replaced with Send for Approval and Some bug fixes | 2023-04-25 | 2023-04-25 | 2hrs | 2hrs | 2023-04-25 | 2023-04-25 | 100% | completed |  | 0
Raj Kumar | 2023-04-29 | 2023-04-26 |  | TS105 | Learning Django | 2023-04-26 | 2023-04-26 | 2hrs | 2hrs | 2023-04-26 | 2023-04-26 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-26 | KSFC | TS106 | Code Review and Push | 2023-04-26 | 2023-04-26 | 2hrs | 2hrs | 2023-04-26 | 2023-04-26 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-26 | KSFC | TS107 | bug fix | 2023-04-26 | 2023-04-26 | 2hrs | 2hrs | 2023-04-26 | 2023-04-26 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-26 | KSFC | TS108 | Testing and Debugging | 2023-04-26 | 2023-04-26 | 2hrs | 2hrs | 2023-04-26 | 2023-04-26 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-27 | KSFC | TS109 | KSFC Deployment | 2023-04-27 | 2023-04-27 | 2hrs | 2hrs | 2023-04-27 | 2023-04-27 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-27 | KSFC | TS110 | Helping Srinivas | 2023-04-27 | 2023-04-27 | 2hrs | 2hrs | 2023-04-27 | 2023-04-27 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-27 | KSFC | TS111 | Add required tabs for Inspection number Under Asset details tab in UC4 | 2023-04-27 | 2023-04-27 | 2hrs | 2hrs | 2023-04-27 | 2023-04-27 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-27 | KSFC | TS112 | Testing and Debugging | 2023-04-27 | 2023-04-27 | 2hrs | 2hrs | 2023-04-27 | 2023-04-27 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-28 |  | TS113 | Learning Django | 2023-04-28 | 2023-04-28 | 2hrs | 2hrs | 2023-04-28 | 2023-04-28 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-28 |  | TS114 | Table Loading bug checking | 2023-04-28 | 2023-04-28 | 2hrs | 2hrs | 2023-04-28 | 2023-04-28 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-28 |  | TS115 | Helping Srinivas | 2023-04-28 | 2023-04-28 | 2hrs | 2hrs | 2023-04-28 | 2023-04-28 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-28 | KSFC | TS116 | Change requirement in last two tabs of UC4 (KSFC) | 2023-04-28 | 2023-04-28 | 2hrs | 2hrs | 2023-04-28 | 2023-04-28 | 100% | completed
Raj Kumar | 2023-04-29 | 2023-04-29 |  | TS117 | Table Loading bug checking | 2023-04-28 | 2023-04-28 | 1hrs | 1hrs | 2023-04-28 | 2023-04-28 | 100% | completed
Raj Kumar |  | 2023-04-30 |  |  | Sunday
Raj Kumar |  | 2023-05-01 |  |  | World Labour Day
Raj Kumar | 2023-05-06 | 2023-05-02 |  | TS118 | Developing New Django Project | 2023-05-02 | 2023-05-02 | 2hrs | 2hrs | 2023-05-02 | 2023-05-02 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-02 |  | TS119 | The attribute 'Aquired Date' is autopopulated to the date when the data is created. | 2023-05-02 | 2023-05-02 | 2hrs | 2hrs | 2023-05-02 | 2023-05-02 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-02 |  | TS120 | Helping Srinivas | 2023-05-02 | 2023-05-02 | 2hrs | 2hrs | 2023-05-02 | 2023-05-02 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-02 |  | TS121 | Acquire status and Release status change requirement in all tabs | 2023-05-02 | 2023-05-02 | 2hrs | 2hrs | 2023-05-02 | 2023-05-02 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-03 |  | TS122 | My Day Bug fix | 2023-05-03 | 2023-05-03 | 2hrs | 2hrs | 2023-05-03 | 2023-05-03 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-03 |  | TS123 | Karmani Bug Fix | 2023-05-03 | 2023-05-03 | 2hrs | 2hrs | 2023-05-03 | 2023-05-03 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-03 |  | TS124 | Creating an api to fetch list of unit names and its corresponding loan number and serial number | 2023-05-03 | 2023-05-03 | 2hrs | 2hrs | 2023-05-03 | 2023-05-03 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-03 |  | TS125 | Learning Django | 2023-05-03 | 2023-05-03 | 2hrs | 2hrs | 2023-05-03 | 2023-05-03 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-04 |  | TS126 | Karmani deployment and testing | 2023-05-04 | 2023-05-04 | 1hrs | 1hrs | 2023-05-04 | 2023-05-04 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-04 |  | TS127 | My Day Add entity code refactor | 2023-05-04 | 2023-05-04 | 4hrs | 4hrs | 2023-05-04 | 2023-05-04 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-04 |  | TS128 | KSFC requirement meeting | 2023-05-04 | 2023-05-04 | 2hrs | 2hrs | 2023-05-04 | 2023-05-04 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-04 |  | TS129 | Learning Django | 2023-05-04 | 2023-05-04 | 1hrs | 1hrs | 2023-05-04 | 2023-05-04 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-05 |  | TS130 | Data table Loading issue | 2023-05-05 | 2023-05-05 | 4hrs | 4hrs | 2023-05-05 | 2023-05-05 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-05 |  | TS131 | Added new Accordian for Land Inspection | 2023-05-05 | 2023-05-05 | 2hrs | 2hrs | 2023-05-05 | 2023-05-05 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-05 |  | TS132 | Helping Srinivas | 2023-05-05 | 2023-05-05 | 2hrs | 2hrs | 2023-05-05 | 2023-05-05 | 100% | completed
Raj Kumar | 2023-05-06 | 2023-05-06 |  |  | Saturday | 2023-05-06 | 2023-05-06 |  |  | 2023-05-06 | 2023-05-06 | 100% | completed
Raj Kumar |  | 2023-05-07 |  |  | Sunday | 2023-05-07 | 2023-05-07 |  |  | 2023-05-07 | 2023-05-07 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-08 |  | TS134 | Added Land Inspection Accordian in UC-4 | 2023-05-08 | 2023-05-08 | 2hrs | 2hrs | 2023-05-08 | 2023-05-08 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-08 |  | TS135 | Added Building Inspection Accordian in UC-4 | 2023-05-08 | 2023-05-08 | 2hrs | 2hrs | 2023-05-08 | 2023-05-08 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-08 |  | TS136 | Added Furniture Inspection Accordian in UC-4 | 2023-05-08 | 2023-05-08 | 2hrs | 2hrs | 2023-05-08 | 2023-05-08 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-08 |  | TS137 | Added Indegenous machinery Inspection in UC-4 | 2023-05-08 | 2023-05-08 | 2hrs | 2hrs | 2023-05-08 | 2023-05-08 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-09 |  | TS138 | Added Imported Machinery Inspection in UC-4 | 2023-05-09 | 2023-05-09 | 2hrs | 2hrs | 2023-05-09 | 2023-05-09 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-09 |  | TS139 | UI Bug fix in Asset Details of UC-4 | 2023-05-09 | 2023-05-09 | 2hrs | 2hrs | 2023-05-09 | 2023-05-09 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-09 |  | TS140 | Created New Tab for Release Adjustment amount in UC-6 | 2023-05-09 | 2023-05-09 | 2hrs | 2hrs | 2023-05-09 | 2023-05-09 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-09 |  | TS141 | Add Charges UI Design | 2023-05-09 | 2023-05-09 | 2hrs | 2hrs | 2023-05-09 | 2023-05-09 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-10 |  | TS142 | Add Issue Return Code refactor | 2023-05-10 | 2023-05-10 | 4hrs | 4hrs | 2023-05-10 | 2023-05-10 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-10 |  | TS143 | Add Issue Testing And debugging | 2023-05-10 | 2023-05-10 | 2hrs | 2hrs | 2023-05-10 | 2023-05-10 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-10 |  | TS144 | Add Issue Return Functional Testing | 2023-05-10 | 2023-05-10 | 2hrs | 2hrs | 2023-05-10 | 2023-05-10 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-11 |  | TS145 | Building Inspection Data table bug fix | 2023-05-11 | 2023-05-11 | 2hrs | 2hrs | 2023-05-11 | 2023-05-11 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-11 |  | TS146 | UC-8 requirement discussion | 2023-05-11 | 2023-05-11 | 3hrs | 3hrs | 2023-05-11 | 2023-05-11 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-11 |  | TS147 | UC-8 requirement implementation | 2023-05-11 | 2023-05-11 | 3hrs | 3hrs | 2023-05-11 | 2023-05-11 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-12 |  | TS148 | Deployed application UC-1 & UC-4 bug fix | 2023-05-12 | 2023-05-12 | 2hrs | 2hrs | 2023-05-12 | 2023-05-12 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-12 |  | TS149 | UC-1 hypothetication deed update bug fix | 2023-05-12 | 2023-05-12 | 2hrs | 2hrs | 2023-05-12 | 2023-05-12 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-12 |  | TS150 | UC-4 UI bug fixes | 2023-05-12 | 2023-05-12 | 2hrs | 2hrs | 2023-05-12 | 2023-05-12 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-12 |  | TS151 | Testing | 2023-05-12 | 2023-05-12 | 2hrs | 2hrs | 2023-05-12 | 2023-05-12 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-13 |  | TS152 | KSFC Meeting | 2023-05-13 | 2023-05-13 | 2hrs | 2hrs | 2023-05-13 | 2023-05-13 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-13 |  | TS153 | Helping Srinivas | 2023-05-13 | 2023-05-13 | 2hrs | 2hrs | 2023-05-13 | 2023-05-13 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-13 |  | TS154 | UC-8 Release Adjustment UI Design | 2023-05-13 | 2023-05-13 | 2hrs | 2hrs | 2023-05-13 | 2023-05-13 | 100% | completed
Raj Kumar | 2023-05-13 | 2023-05-13 |  | TS155 | UC-8 Backend Code refactor | 2023-05-13 | 2023-05-13 | 2hrs | 2hrs | 2023-05-13 | 2023-05-13 | 100% | completed
Raj Kumar | 2023-05-14 | 2023-05-14 |  |  | Sunday
Raj Kumar | 2023-05-20 | 2023-05-15 |  | TS156 | UC-8 Release Adjustment Backend Bug Fix | 2023-05-15 | 2023-05-15 | 3hrs | 3hrs | 2023-05-15 | 2023-05-15 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-15 |  | TS157 | UC-8 Proposal Details Bug fix | 2023-05-15 | 2023-05-15 | 3hrs | 3hrs | 2023-05-15 | 2023-05-15 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-15 |  | TS158 | UC-5 (If the Land is Financed by the KSFC only then the Land Inspection Tab will enabled other wise if the user clicks on Land Tab the system should pop-up a message that the Land is not Financed ) | 2023-05-15 | 2023-05-15 | 2hrs | 2hrs | 2023-05-15 | 2023-05-15 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-16 |  | TS159 | Karmani Download All Survey by filter api implementation | 2023-05-16 | 2023-05-16 | 2hrs | 2hrs | 2023-05-16 | 2023-05-16 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-16 |  | TS160 | Testing And debugging | 2023-05-16 | 2023-05-16 | 4hrs | 4hrs | 2023-05-16 | 2023-05-16 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-16 |  | TS161 | Karmani Deployment | 2023-05-16 | 2023-05-16 | 1hrs | 1hrs | 2023-05-16 | 2023-05-16 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-17 |  | TS162 | KSFC Meeting | 2023-05-17 | 2023-05-17 | 1hrs | 1hrs | 2023-05-17 | 2023-05-17 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-17 |  | TS163 | Helping Srinivas | 2023-05-17 | 2023-05-17 | 3hrs | 3hrs | 2023-05-17 | 2023-05-17 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-17 |  | TS164 | UC-8 Add proposal UI Chnages | 2023-05-17 | 2023-05-17 | 2hrs | 2hrs | 2023-05-17 | 2023-05-17 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-18 |  | TS165 | SonarQube setup | 2023-05-18 | 2023-05-18 | 2hrs | 2hrs | 2023-05-18 | 2023-05-18 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-18 |  | TS166 | Helping Srinivas & Jayanth | 2023-05-18 | 2023-05-18 | 2hrs | 2hrs | 2023-05-18 | 2023-05-18 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-18 |  | TS167 | Execution of sonarqube on KSFC.UI project | 2023-05-18 | 2023-05-18 | 3hrs | 3hrs | 2023-05-18 | 2023-05-18 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-19 |  | TS168 | KSFC Meeting with Anand Sir | 2023-05-19 | 2023-05-19 | 3hrs | 3hrs | 2023-05-19 | 2023-05-19 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-19 |  | TS169 | Preparation of flow chart | 2023-05-19 | 2023-05-19 | 3hrs | 3hrs | 2023-05-19 | 2023-05-19 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-19 |  | TS170 | Employee and unit name relation research | 2023-05-19 | 2023-05-19 | 2hrs | 2hrs | 2023-05-19 | 2023-05-19 | 100% | completed
Raj Kumar | 2023-05-20 | 2023-05-20 |  |  | Saturday
Raj Kumar | 2023-05-21 | 2023-05-21 |  |  | Sunday
Raj Kumar | 2023-05-27 | 2023-05-22 |  | TS180 | BOCW Project Setup | 2023-05-22 | 2023-05-22 | 2hrs | 2hrs | 2023-05-22 | 2023-05-22 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-22 |  | TS181 | Move Inline Javasacript in Payments Module | 2023-05-22 | 2023-05-22 | 1hrs | 1hrs | 2023-05-22 | 2023-05-22 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-22 |  | TS182 | Add Payment Bug fix | 2023-05-22 | 2023-05-22 | 2hrs | 2hrs | 2023-05-22 | 2023-05-22 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-22 |  | TS183 | Edit Payment Bug fix | 2023-05-22 | 2023-05-22 | 2hrs | 2hrs | 2023-05-22 | 2023-05-22 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-23 |  | TS184 | Preparation of Design Document | 2023-05-23 | 2023-05-23 | 2hrs | 2hrs | 2023-05-23 | 2023-05-23 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-23 |  | TS185 | Wrote query to fetch all Survey answers along with basic details | 2023-05-23 | 2023-05-23 | 2hrs | 2hrs | 2023-05-23 | 2023-05-23 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-23 |  | TS186 | Conversion from sql to linq query and integrate the same in karmani api project | 2023-05-23 | 2023-05-23 | 2hrs | 2hrs | 2023-05-23 | 2023-05-23 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-23 |  | TS187 | Karmani Deploymnet,Debugging and testing | 2023-05-23 | 2023-05-23 | 2hrs | 2hrs | 2023-05-23 | 2023-05-23 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-24 |  | TS188 | Make the field of Agreement # in Add Issue/Return as Input field | 2023-05-24 | 2023-05-24 | 3hrs | 3hrs | 2023-05-24 | 2023-05-24 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-24 |  | TS189 | Debugging and Testing | 2023-05-24 | 2023-05-24 | 2hrs | 2hrs | 2023-05-24 | 2023-05-24 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-24 |  | TS190 | Add Phone number field in Edit Entity | 2023-05-24 | 2023-05-24 | 3hrs | 3hrs | 2023-05-24 | 2023-05-24 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-25 |  | TS191 | Block Diagarm for My Day Web | 2023-05-25 | 2023-05-25 | 4hrs | 4hrs | 2023-05-25 | 2023-05-25 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-25 |  | TS192 | Block Diagram for My Day Mobile | 2023-05-25 | 2023-05-25 | 4hrs | 4hrs | 2023-05-25 | 2023-05-25 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-26 |  | TS193 | Prepare a document to setup karmani ui and api | 2023-05-26 | 2023-05-26 | 2hrs | 2hrs | 2023-05-26 | 2023-05-26 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-26 |  | TS194 | Prepare Block diagram of karmani project | 2023-05-26 | 2023-05-26 | 3hrs | 3hrs | 2023-05-26 | 2023-05-26 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-26 |  | TS195 | Prepare Architecture diagram of karmani | 2023-05-26 | 2023-05-26 | 3hrs | 3hrs | 2023-05-26 | 2023-05-26 | 100% | completed
Raj Kumar | 2023-05-27 | 2023-05-27 |  |  | Saturday
Raj Kumar | 2023-05-28 | 2023-05-28 |  |  | Sunday
Raj Kumar | 2023-06-03 | 2023-05-29 |  |  | Monday
Raj Kumar | 2023-06-03 | 2023-05-30 |  |  | Tuesday
Raj Kumar | 2023-06-03 | 2023-05-31 |  |  | Wednesday
Raj Kumar | 2023-06-03 | 2023-06-01 |  |  | Thursday
Raj Kumar | 2023-06-03 | 2023-06-02 | My day | TS196 | Cluster is not laoding Bug fix in Add Issue Return Bug fix | 2023-06-02 | 2023-06-02 | 3hrs | 3hrs | 2023-06-02 | 2023-06-02 | 100% | completed
Raj Kumar | 2023-06-03 | 2023-06-02 | Project Over Sight | TS197 | Project Setup and Login UI Design (ProjectOverSight) | 2023-06-02 | 2023-06-02 | 2hrs | 2hrs | 2023-06-02 | 2023-06-02 | 100% | completed
Raj Kumar | 2023-06-03 | 2023-06-02 | Project Over Sight | TS198 | Implementing Login and pushed the code to bit bucket (ProjectOverSight) | 2023-06-02 | 2023-06-02 | 3hrs | 3hrs | 2023-06-02 | 2023-06-02 | 100% | completed
Raj Kumar | 2023-06-03 | 2023-06-03 | My day | TS199 | URL Resolver Code Setup and Code set up documentation | 2023-06-03 | 2023-06-03 | 2hrs | 2hrs | 2023-06-03 | 2023-06-03 | 100% | completed
Raj Kumar | 2023-06-03 | 2023-06-03 | Project Over Sight | TS200 | Login Validation | 2023-06-03 | 2023-06-03 | 2hrs | 2hrs | 2023-06-03 | 2023-06-03 | 100% | completed
Raj Kumar | 2023-06-03 | 2023-06-03 | Project Over Sight | TS201 | Create routes for employee and admin Login | 2023-06-03 | 2023-06-03 | 2hrs | 2hrs | 2023-06-03 | 2023-06-03 | 100% | completed
Raj Kumar | 2023-06-04 | 2023-06-04 |  |  | Sunday
Raj Kumar | 2023-06-10 | 2023-06-05 | My day | TS202 | Need to get KT on PJMargo Expense Excel tool for Marketing and Preaparing the Requirement Document | 2023-06-05 | 2023-06-05 | 2hrs | 2hrs | 2023-06-05 | 2023-06-05 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-05 | Project Over Sight | TS203 | Make The project UI responsive (ProjectOverSight) | 2023-06-05 | 2023-06-05 | 3hrs | 3hrs | 2023-06-05 | 2023-06-05 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-05 | Project Over Sight | TS204 | Employee Dashboard Card Design (ProjectOverSight) | 2023-06-05 | 2023-06-05 | 3hrs | 3hrs | 2023-06-05 | 2023-06-05 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-06 | My day | TS205 | Watching my day training Videos | 2023-06-06 | 2023-06-06 | 4hrs | 4hrs | 2023-06-06 | 2023-06-06 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-06 | Project Over Sight | TS206 | Create Project List UI and Bind Data to it | 2023-06-06 | 2023-06-06 | 2hrs | 2hrs | 2023-06-06 | 2023-06-06 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-06 | Project Over Sight | TS207 | When name in project list is clicked popup should appear | 2023-06-06 | 2023-06-06 | 2hrs | 2hrs | 2023-06-06 | 2023-06-06 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-07 | Project Over Sight | TS208 | Created filter box UI (project Over Sight) | 2023-06-07 | 2023-06-07 | 3hrs | 3hrs | 2023-06-07 | 2023-06-07 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-07 | Project Over Sight | TS209 | Implemented filter functionalaty (Project Over Sight) | 2023-06-07 | 2023-06-07 | 3hrs | 3hrs | 2023-06-07 | 2023-06-07 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-07 | Project Over Sight | TS210 | List of Tasks Table refactor | 2023-06-07 | 2023-06-07 | 2hrs | 2hrs | 2023-06-07 | 2023-06-07 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-08 | Project Over Sight | TS211 | Filter Box redesign | 2023-06-08 | 2023-06-08 | 2hrs | 2hrs | 2023-06-08 | 2023-06-08 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-08 | Project Over Sight | TS212 | Code refactor | 2023-06-08 | 2023-06-08 | 2hrs | 2hrs | 2023-06-08 | 2023-06-08 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-08 | Project Over Sight | TS213 | Implemented filter functionalaty (Project Over Sight) | 2023-06-08 | 2023-06-08 | 2hrs | 2hrs | 2023-06-08 | 2023-06-08 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-09 | Project Over Sight | TS214 | Show User name in top bar once logged in , Login validations | 2023-06-09 | 2023-06-09 | 3hrs | 3hrs | 2023-06-09 | 2023-06-09 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-09 | Project Over Sight | TS215 | Add Employee POPUP design,code Review | 2023-06-09 | 2023-06-09 | 1hrs | 1hrs | 2023-06-09 | 2023-06-09 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-09 | Project Over Sight | TS216 | Implemented Download functionality for tasklist and progress list | 2023-06-09 | 2023-06-09 | 2hrs | 2hrs | 2023-06-09 | 2023-06-09 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-10 | Project Over Sight | TS217 | Filter box redesign | 2023-06-10 | 2023-06-10 | 2hrs | 2hrs | 2023-06-10 | 2023-06-10 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-10 | Project Over Sight | TS218 | Making the routes authorized | 2023-06-10 | 2023-06-10 | 2hrs | 2hrs | 2023-06-10 | 2023-06-10 | 100% | completed
Raj Kumar | 2023-06-10 | 2023-06-10 | Project Over Sight | TS219 | Quadrant Design for Admin Dashboard | 2023-06-10 | 2023-06-10 | 2hrs | 2hrs | 2023-06-10 | 2023-06-10 | 100% | completed
| 2023-06-11 | 2023-06-11 |  |  | Sunday
Raj Kumar | 2023-06-17 | 2023-06-12 | Project Over Sight | TS220 | Employee Screen data table Implementation | 2023-06-12 | 2023-06-12 | 3hrs | 3hrs | 2023-06-12 | 2023-06-12 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-12 | Project Over Sight | TS221 | Employee Filtter implementation Implementation | 2023-06-12 | 2023-06-12 | 3hrs | 3hrs | 2023-06-12 | 2023-06-12 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-12 | Project Over Sight | TS222 | Add Employee Implementation | 2023-06-12 | 2023-06-12 | 2hrs | 2hrs | 2023-06-12 | 2023-06-12 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-13 | Project Over Sight | TS223 | Edit employee UI and functionality Implementation | 2023-06-13 | 2023-06-13 | 3hrs | 3hrs | 2023-06-13 | 2023-06-13 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-13 | Project Over Sight | TS224 | Assign TaskmUi and functionality Implementation | 2023-06-13 | 2023-06-13 | 3hrs | 3hrs | 2023-06-13 | 2023-06-13 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-13 | Project Over Sight | TS225 | Drawer Implementation | 2023-06-13 | 2023-06-13 | 2hrs | 2hrs | 2023-06-13 | 2023-06-13 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-14 | Project Over Sight | TS226 | Assign Task Implementation | 2023-06-14 | 2023-06-14 | 3hrs | 3hrs | 2023-06-14 | 2023-06-14 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-14 | Project Over Sight | TS227 | Add employee Ui new Field Added Bug fix | 2023-06-14 | 2023-06-14 | 2.5hrs | 2.5hrs | 2023-06-14 | 2023-06-14 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-14 | Project Over Sight | TS228 | Edit Employee Implementation | 2023-06-14 | 2023-06-14 | 2.5hrs | 2.5hrs | 2023-06-14 | 2023-06-14 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-15 | Project Over Sight | TS229 | Add Project Ui Design and Implementation | 2023-06-15 | 2023-06-15 | 2hrs | 2hrs | 2023-06-15 | 2023-06-15 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-15 | Project Over Sight | TS230 | View Project UI Design and Implementation | 2023-06-15 | 2023-06-15 | 2hrs | 2hrs | 2023-06-15 | 2023-06-15 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-15 | Project Over Sight | TS231 | Edit employee bug fix,Project filter UI alignment | 2023-06-15 | 2023-06-15 | 2hrs | 2hrs | 2023-06-15 | 2023-06-15 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-15 | Project Over Sight | TS232 | Edit Project UI Design And Implementation | 2023-06-15 | 2023-06-15 | 2hrs | 2hrs | 2023-06-15 | 2023-06-16 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-16 | Project Over Sight | TS233 | Edit Project Bug Fix - 2hrs | 2023-06-16 | 2023-06-16 | 2hrs | 2hrs | 2023-06-16 | 2023-06-16 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-16 | Project Over Sight | TS234 | Project Quadrant data binding - 3hrs | 2023-06-16 | 2023-06-16 | 2hrs | 2hrs | 2023-06-16 | 2023-06-16 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-16 | Project Over Sight | TS235 | Assign And Unassign Employee skill list Ui design and data binding - 3hrs | 2023-06-16 | 2023-06-16 | 2hrs | 2hrs | 2023-06-16 | 2023-06-16 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-17 | Project Over Sight | TS236 | serach and assign employee skill | 2023-06-17 | 2023-06-17 | 2hrs | 2hrs | 2023-06-17 | 2023-06-17 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-17 | Project Over Sight | TS237 | Bind the UI for objective list with add and edit and filter | 2023-06-17 | 2023-06-17 | 2hrs | 2hrs | 2023-06-17 | 2023-06-17 | 100% | completed
Raj Kumar | 2023-06-17 | 2023-06-17 | Project Over Sight | TS238 | Assign Skill Ui Design | 2023-06-17 | 2023-06-17 | 2hrs | 2hrs | 2023-06-17 | 2023-06-17 | 100% | completed
Raj Kumar | 2023-06-18 | 2023-06-18 |  |  | Sunday
Raj Kumar | 2023-06-24 | 2023-06-19 | Project Over Sight | TS239 | Create an UI for assign and unassign team member | 2023-06-19 | 2023-06-19 | 2.5hrs | 2.5hrs | 2023-06-19 | 2023-06-19 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-19 | Project Over Sight | TS240 | Implement assign and unassign team member | 2023-06-19 | 2023-06-19 | 3hrs | 3hrs | 2023-06-19 | 2023-06-19 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-19 | Project Over Sight | TS241 | Write post method for assign and unassign team member | 2023-06-19 | 2023-06-19 | 2.5hrs | 2.5hrs | 2023-06-19 | 2023-06-19 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-20 | Project Over Sight | TS242 | .Design Ui for Team Quadrant | 2023-06-20 | 2023-06-20 | 2.5hrs | 2.5hrs | 2023-06-20 | 2023-06-20 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-20 | Project Over Sight | TS243 | Implementation of team quadrant | 2023-06-20 | 2023-06-20 | 2.5hrs | 2.5hrs | 2023-06-20 | 2023-06-20 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-20 | Project Over Sight | TS244 | Writeing an api to bind data to team quadrant | 2023-06-20 | 2023-06-20 | 3hrs | 3hrs | 2023-06-20 | 2023-06-20 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-21 | Project Over Sight | TS245 | Team quadrant | 2023-06-21 | 2023-06-21 | 2.5hrs | 2.5hrs | 2023-06-21 | 2023-06-21 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-21 | Project Over Sight | TS246 | query change for team members | 2023-06-21 | 2023-06-21 | 2.5hrs | 2.5hrs | 2023-06-21 | 2023-06-21 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-21 | Project Over Sight | TS247 | bug fix in project for null handling | 2023-06-21 | 2023-06-21 | 3hrs | 3hrs | 2023-06-21 | 2023-06-21 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-21 | Project Over Sight | TS248 | map the employee to the project | 2023-06-21 | 2023-06-21 | 2.5hrs | 2.5hrs | 2023-06-21 | 2023-06-21 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-22 | Project Over Sight | TS249 | Ad WeekEndingDate filter in task quadrant | 2023-06-22 | 2023-06-22 | 2.5hrs | 2.5hrs | 2023-06-22 | 2023-06-22 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-22 | Project Over Sight | TS250 | US count & UI count & Total Task count & not started Task count & in Progress Count in Project List | 2023-06-22 | 2023-06-22 | 3hrs | 3hrs | 2023-06-22 | 2023-06-22 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-22 | Project Over Sight | TS251 | onclick of employee name in Task Quadrant it should redirect to Task list with employee name and WeekEnding Date filter | 2023-06-22 | 2023-06-22 | 2.5hrs | 2.5hrs | 2023-06-22 | 2023-06-22 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-23 | Project Over Sight | TS252 | . Use case and user interface,WEEKENDING DATE ,comment column should appear in grid and filter box | 2023-06-23 | 2023-06-23 | 2.5hrs | 2.5hrs | 2023-06-23 | 2023-06-23 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-23 | Project Over Sight | TS253 | Add on hold option in Status of Task Filter & Team name should be drop down in Task list filter | 2023-06-23 | 2023-06-23 | 3hrs | 3hrs | 2023-06-23 | 2023-06-23 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-23 | Project Over Sight | TS254 | Assign lead Implementation | 2023-06-23 | 2023-06-23 | 2.5hrs | 2.5hrs | 2023-06-23 | 2023-06-23 | 100% | completed
Raj Kumar | 2023-06-24 | 2023-06-24 | Saturday
Raj Kumar | 2023-06-25 | 2023-06-25 | Sunday
Raj Kumar | 2023-07-01 | 2023-06-26 | Project Over Sight | TS255 | React Js Class Room - 4hrs | 2023-06-26 | 2023-06-26 | 4hrs | 4hrs | 2023-06-26 | 2023-06-26 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-26 | Project Over Sight | TS256 | unit testing 2 hrs - 2hrs | 2023-06-26 | 2023-06-26 | 2hrs | 2hrs | 2023-06-26 | 2023-06-26 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-26 | Project Over Sight | TS257 | onclick of employee name in Task Quadrant it should redirect to Task | 2023-06-26 | 2023-06-26 | 1hrs | 1hrs | 2023-06-26 | 2023-06-26 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-26 | Project Over Sight | TS258 | list with employee name and WeekEnding Date filter - 2hrs | 2023-06-26 | 2023-06-26 | 1hrs | 1hrs | 2023-06-26 | 2023-06-26 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-27 | Project Over Sight | TS259 |  | 2023-06-27 | 2023-06-27 |  |  | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-27 | Project Over Sight | TS260 |  | 2023-06-27 | 2023-06-27 |  |  | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-27 | Project Over Sight | TS261 |  | 2023-06-27 | 2023-06-27 |  |  | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-27 | Project Over Sight | TS262 |  | 2023-06-27 | 2023-06-27 |  |  | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-28 | Project Over Sight | TS263 | User Interface and Assign Employee Bug Fix | 2023-06-27 | 2023-06-28 | 2hrs | 2hrs | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-28 | Project Over Sight | TS264 | 2. Task List UI Design And Implementation in Employee Dashboard | 2023-06-27 | 2023-06-28 | 2hrs | 2hrs | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-28 | Project Over Sight | TS265 | 3. Task Progress List UI Design And Implementation in Employee Dashboard | 2023-06-27 | 2023-06-28 | 2hrs | 2hrs | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-28 | Project Over Sight | TS266 | 4. Project List UI Design And Implementation in Employee Dashboard - | 2023-06-27 | 2023-06-28 | 2hrs | 2hrs | 2023-06-27 | 2023-06-27 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-29 | Project Over Sight | TS267 | API to Assign task team member | 2023-06-29 | 2023-06-29 | 2hrs | 2hrs | 2023-06-29 | 2023-06-29 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-29 | Project Over Sight | TS268 | 2. Data table Redesign | 2023-06-29 | 2023-06-29 | 2hrs | 2hrs | 2023-06-29 | 2023-06-29 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-29 | Project Over Sight | TS269 | 3. Testing and Debugging | 2023-06-29 | 2023-06-29 | 2hrs | 2hrs | 2023-06-29 | 2023-06-29 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-29 | Project Over Sight | TS270 | 4. Task Progress Download Implementation, Bug Fixes | 2023-06-29 | 2023-06-29 | 2hrs | 2hrs | 2023-06-29 | 2023-06-29 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-30 | Project Over Sight | TS271 | Employee Attendance UI desing | 2023-06-30 | 2023-06-30 | 3hrs | 3hrs | 2023-06-30 | 2023-06-30 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-30 | Project Over Sight | TS272 | Employee Attendance API Implementation | 2023-06-30 | 2023-06-30 | 3hrs | 3hrs | 2023-06-30 | 2023-06-30 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-06-30 | Project Over Sight | TS273 | Testing and Debugging | 2023-06-30 | 2023-06-30 | 2hrs | 2hrs | 2023-06-30 | 2023-06-30 | 100% | completed
Raj Kumar | 2023-07-01 | 2023-07-01 | Saturday
Raj Kumar | 2023-07-02 | 2023-07-02 | Sunday
Raj Kumar | 2023-07-08 | 2023-07-03 | Project Over Sight | TS274 | 1. Individual Employee Attendence UI Design API Binding | 2023-07-03 | 2023-07-03 | 3hrs | 3hrs | 2023-07-03 | 2023-07-03 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-03 | Project Over Sight | TS275 | 2. Writing a linq query to fetch individual and multiple Employee attendance | 2023-07-03 | 2023-07-03 | 2.5hrs | 2.5hrs | 2023-07-03 | 2023-07-03 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-03 | Project Over Sight | TS276 | 3. Dual List box items should be in Alphabetical Order | 2023-07-03 | 2023-07-03 | 2.5hrs | 2.5hrs | 2023-07-03 | 2023-07-03 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-04 | Project Over Sight | TS277 | Add Search Filter for Dual List Box | 2023-07-04 | 2023-07-04 | 2hrs | 2hrs | 2023-07-04 | 2023-07-04 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-04 | Project Over Sight | TS278 | 2. Google map integration for In Time Location & out Time Location | 2023-07-04 | 2023-07-04 | 2hrs | 2hrs | 2023-07-04 | 2023-07-04 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-04 | Project Over Sight | TS279 | 3. Data table Ui Bug fix and task list bug fix | 2023-07-04 | 2023-07-04 | 2hrs | 2hrs | 2023-07-04 | 2023-07-04 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-04 | Project Over Sight | TS280 | 4. Comment Screen UI | 2023-07-04 | 2023-07-04 | 2hrs | 2hrs | 2023-07-04 | 2023-07-04 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-05 | Project Over Sight | TS281 | API to fetch EmployeeTask Comments - 2hrs | 2023-07-05 | 2023-07-05 | 2hrs | 2hrs | 2023-07-05 | 2023-07-05 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-05 | Project Over Sight | TS282 | 2. API to fetch EmployeeDailyTask Comments - 2hrs | 2023-07-05 | 2023-07-05 | 2hrs | 2hrs | 2023-07-05 | 2023-07-05 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-05 | Project Over Sight | TS283 | 3. UI for EmployeeTask Comment - 2hrs | 2023-07-05 | 2023-07-05 | 2hrs | 2hrs | 2023-07-05 | 2023-07-05 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-05 | Project Over Sight | TS284 | 4. UI for EmployeeDailsyTask Comment - 2hrs | 2023-07-05 | 2023-07-05 | 2hrs | 2hrs | 2023-07-05 | 2023-07-05 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-06 | Project Over Sight | TS285 | 1. Bind data to employee time comments | 2023-07-06 | 2023-07-06 | 3hrs | 3hrs | 2023-07-06 | 2023-07-06 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-06 | Project Over Sight | TS286 | 2. bind assign hours available hour unassign and bind search filter for weekend date team quadrant | 2023-07-06 | 2023-07-06 | 2.5hrs | 2.5hrs | 2023-07-06 | 2023-07-06 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-06 | Project Over Sight | TS287 | 3. Testing and Debugging | 2023-07-06 | 2023-07-06 | 2.5hrs | 2.5hrs | 2023-07-06 | 2023-07-06 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-06-07 | Project Over Sight | TS288 | Create Team Object List UI with list and Filter and API to fetch the list | 2023-06-07 | 2023-06-07 | 3hrs | 3hrs | 2023-06-07 | 2023-06-07 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-06-07 | Project Over Sight | TS289 | 2. Add Team Objective UI and implementation | 2023-06-07 | 2023-06-07 | 2.5hrs | 2.5hrs | 2023-06-07 | 2023-06-07 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-06-07 | Project Over Sight | TS290 | 3. Edit and view Team Objective list UI and implementation | 2023-06-07 | 2023-06-07 | 2.5hrs | 2.5hrs | 2023-06-07 | 2023-06-07 | 100% | completed
Raj Kumar | 2023-07-08 | 2023-07-08 |  |  | Saturaday
Raj Kumar | 2023-07-09 | 2023-07-09 |  |  | Sunday
Raj Kumar | 2023-07-10 | 2023-07-10 |  |  | Monday
Raj Kumar | 2023-07-11 | 2023-07-11 | Project Over Sight | TS291 | 1.versiom details should appeare in project project | 2023-07-11 | 2023-07-11 | 2hrs | 2hrs | 2023-07-11 | 2023-07-11 | 100% | completed
Raj Kumar | 2023-07-11 | 2023-07-11 | Project Over Sight | TS292 | 2.scroll bar fix in table | 2023-07-11 | 2023-07-11 | 2hrs | 2hrs | 2023-07-11 | 2023-07-11 | 100% | completed
Raj Kumar | 2023-07-11 | 2023-07-11 | Project Over Sight | TS293 | 3.paging implementation | 2023-07-11 | 2023-07-11 | 2hrs | 2hrs | 2023-07-11 | 2023-07-11 | 100% | completed
Raj Kumar | 2023-07-11 | 2023-07-11 | Project Over Sight | TS294 | 4.weekly plan task big fix | 2023-07-11 | 2023-07-11 | 2hrs | 2hrs | 2023-07-11 | 2023-07-11 | 100% | completed
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar
Raj Kumar